## Day Rates
Illustrative Day Rates — practice-exercise placeholders, not any real agency's actual published rates
Role | Illustrative Rate / Day (USD)
Business Analyst / Project Lead | 450
UX Designer | 400
UI Designer | 400
Backend Developer | 450
Frontend Developer | 450
QA Engineer | 350
Delivery / Account Manager | 500

## Estimate
Phase | Role | Days | Rate / Day | Cost
0 — Discovery & Governance Alignment | Business Analyst / Project Lead | 10 | 450 | 4500
0 — Discovery & Governance Alignment | Delivery / Account Manager | 2 | 500 | 1000
1 — UX Design | Business Analyst / Project Lead | 5 | 450 | 2250
1 — UX Design | UX Designer | 15 | 400 | 6000
2 — UI Design | UI Designer | 10 | 400 | 4000
2 — UI Design | Business Analyst / Project Lead | 2 | 450 | 900
3 — Development | Backend Developer | 30 | 450 | 13500
3 — Development | Frontend Developer | 30 | 450 | 13500
3 — Development | Business Analyst / Project Lead | 6 | 450 | 2700
4 — QA & Testing | QA Engineer | 10 | 350 | 3500
4 — QA & Testing | Business Analyst / Project Lead | 2 | 450 | 900
4 — QA & Testing | Backend Developer | 3 | 450 | 1350
4 — QA & Testing | Frontend Developer | 3 | 450 | 1350
5 — Pilot Launch | Business Analyst / Project Lead | 8 | 450 | 3600
5 — Pilot Launch | QA Engineer | 4 | 350 | 1400
5 — Pilot Launch | Backend Developer | 3 | 450 | 1350
5 — Pilot Launch | Frontend Developer | 3 | 450 | 1350
6 — Full Rollout | Business Analyst / Project Lead | 6 | 450 | 2700
6 — Full Rollout | Frontend Developer | 3 | 450 | 1350
6 — Full Rollout | Backend Developer | 2 | 450 | 900
6 — Full Rollout | QA Engineer | 3 | 350 | 1050
7 — Hypercare & Review | Business Analyst / Project Lead | 6 | 450 | 2700
7 — Hypercare & Review | Delivery / Account Manager | 2 | 500 | 1000
7 — Hypercare & Review | Backend Developer | 2 | 450 | 900
7 — Hypercare & Review | Frontend Developer | 2 | 450 | 900
| Total | 172 |  | 74650

## Summary by Phase
Phase | Effort (days) | Illustrative Cost
0 — Discovery & Governance Alignment | 12 | 5500
1 — UX Design | 20 | 8250
2 — UI Design | 12 | 4900
3 — Development | 66 | 29700
4 — QA & Testing | 18 | 7100
5 — Pilot Launch | 18 | 7700
6 — Full Rollout | 14 | 6000
7 — Hypercare & Review | 12 | 5500
Total | 172 | 74650
Illustrative figures for a practice RFP-response exercise. Not a real agency's actual rates or a committed quote. Excludes KPI expansion, regulatory reporting integration, and the fifth property — each scoped separately once its dependency resolves.